## GCS
Task | Description | Team Involved | Start Date | End Date
Authentication & Authorization Management | Implement role‑based access control so operators, maintenance staff and users get proper permissions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2025-12-02 | 2025-12-11
UI Panels for Mission Planning | Mission planning UI with DSM + Survey of India data including preprocessing & visualization. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2025-12-12 | 2025-12-23
Data exchange GCS-UGV | Real‑time secure bidirectional communication using MAVLink/ROS for telemetry, commands, diagnostics. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2025-12-24 | 2026-01-02
UI Panels for GCS Operations | Panels for viewing and configuring mission parameters—waypoints, speeds, modes. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-01-05 | 2026-01-14
Notification Messages | Health monitoring alerts, emergency triggers based on thresholds or operator inputs. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-01-15 | 2026-01-27
Communication & Networking Protocols | Define command sets, message structures, networking standards for GCS‑UGV. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-01-28 | 2026-02-06
Alert Pop-Ups | Alerts for mission feasibility, health thresholds, object detection from video. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-02-09 | 2026-02-18
Data Storage & Back Up | Secure storage with retention policies, automatic backups for mission data. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-02-19 | 2026-03-02
Video Recording / Image Snapshot storage | Video recording and image snapshots with indexing & timestamp retrieval. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-03-03 | 2026-03-12
System Health Assessment | Continuous diagnostics, telemetry analysis, health scoring and reporting. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-03-13 | 2026-03-24
Fault Management | Rule‑based fault classification with severity‑based priorities. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-03-25 | 2026-04-03
Emergency Management System | Integrate environmental sensors; automated emergency handling for fault events. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-04-06 | 2026-04-15
Alerts and Notification Management | Central alert system for faults, object detection, emergency conditions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-04-16 | 2026-04-27
Video Processing at GCS | Real‑time video decoding, stitching, overlays and analytics. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-04-28 | 2026-05-08
Pre- & Post Test of UGV Peripherals | Automated tests for PTZ camera, motors, battery, GNSS before/after missions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-05-11 | 2026-05-20
GO / NO GO Decision | Automated go/no‑go based on subsystem health and test results. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-05-21 | 2026-06-01
Return to Home (RTH) | Automatic RTH on system failures or abort conditions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-06-02 | 2026-06-11

## VCU
Task | Description | Team Involved | Start Date | End Date | Status
Initial Power Check | VCU development activity. | Sachin Kate, Borse Team | 2025-12-02 | 2025-12-09 | Scheduled
Linux Installation | VCU development activity. | Sachin Kate, Borse Team | 2025-12-10 | 2025-12-17 | Scheduled
ROS2 Installation | VCU development activity. | Sachin Kate, Borse Team | 2025-12-18 | 2025-12-25 | Scheduled
ROS2 Workspace configuration | VCU development activity. | Sachin Kate, Borse Team | 2025-12-26 | 2026-01-02 | Scheduled
Temperature Sensor – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-01-05 | 2026-01-12 | Scheduled
Temperature Sensor – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-01-13 | 2026-01-20 | Scheduled
Temperature Sensor – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-01-21 | 2026-01-29 | Scheduled
Temperature Sensor – calibration | VCU development activity. | Sachin Kate, Borse Team | 2026-01-30 | 2026-02-06 | Scheduled
Temperature Sensor – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-02-09 | 2026-02-16 | Scheduled
Motor Driver – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-02-17 | 2026-02-24 | Scheduled
Motor Driver – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-02-25 | 2026-03-04 | Scheduled
Motor Driver – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-03-05 | 2026-03-12 | Scheduled
Motor Driver – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-03-13 | 2026-03-20 | Scheduled
3D LIDAR – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-03-23 | 2026-03-30 | Scheduled
3D LIDAR – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-03-31 | 2026-04-07 | Scheduled
3D LIDAR – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-04-08 | 2026-04-15 | Scheduled
3D LIDAR – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-04-16 | 2026-04-23 | Scheduled
Follow Me Tag – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-04-24 | 2026-05-04 | Scheduled
Follow Me Tag – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-05-05 | 2026-05-12 | Scheduled
Follow Me Tag – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-05-13 | 2026-05-20 | Scheduled
Follow Me Tag – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-05-21 | 2026-05-28 | Scheduled
IO module – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-05-29 | 2026-06-05 | Scheduled
IO module – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-06-08 | 2026-06-15 | Scheduled
IO module – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-06-16 | 2026-06-23 | Scheduled
IO module – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-06-24 | 2026-07-01 | Scheduled
EO Sight Camera – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-07-02 | 2026-07-09 | Scheduled
EO Sight Camera – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-07-10 | 2026-07-17 | Scheduled
EO Sight Camera – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-07-20 | 2026-07-27 | Scheduled
EO Sight Camera – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-07-28 | 2026-07-30 | Partial (ends at window end) - needs review
GNSS receiver – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
GNSS receiver – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
GNSS receiver – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EO Sight Camera + encoder – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EO Sight Camera + encoder – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EO Sight Camera + encoder – device testing | Validate real hardware performance and verify output stability. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
Drive camera + encoder – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
Drive camera + encoder – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
Drive camera + encoder – device testing | Validate real hardware performance and verify output stability. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
Radio – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
Radio – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
Radio – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
BMS – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
BMS – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
BMS – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EO Sight Camera Mast – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EO Sight Camera Mast – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EO Sight Camera Mast – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EM brake – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EM brake – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression
EM brake – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team |  |  | Pending - needs parallelization/compression

## Hardware
Task | Description | Team Involved | Start Date | End Date
Sensor Calibration & Validation | Calibrate LiDAR, IMU, GNSS and validate accuracy. | Hardware Team, QA Team | 2025-12-02 | 2025-12-22
Environmental Stress Testing | Thermal and vibration endurance testing. | Hardware Team, QA Team | 2025-12-23 | 2026-01-12
EMI/EMC Testing | Test electromagnetic interference and compatibility. | Hardware Team, QA Team | 2026-01-13 | 2026-02-03
Integration with Firmware | Validate hardware after firmware integration. | Hardware Team, QA Team | 2026-02-04 | 2026-02-24
Field Integration Testing | System field tests for performance validation. | Hardware Team, QA Team | 2026-02-25 | 2026-03-17

## QA
Task | Description | Team Involved | Start Date | End Date
Test Plan Preparation | Create QA plans, test cases and acceptance criteria. | QA Team | 2025-12-02 | 2025-12-22
Functional & Regression Testing | Run functional and regression test suites. | QA Team | 2025-12-23 | 2026-01-12
Bug Triaging & Fix Verification | Triage issues and verify fixes. | QA Team | 2026-01-13 | 2026-02-03
Final QA Sign-off | Prepare documentation and final QA approval. | QA Team | 2026-02-04 | 2026-02-24

## PMO
Task | Description | Team Involved | Start Date | End Date
Project Kick-off | Project initiation and resource planning. | PMO Team | 2025-12-02 | 2025-12-22
Weekly Sprint Reviews | Weekly progress reviews, impediment removal, stakeholder updates. | PMO Team | 2025-12-01 | 2026-07-30
Mid-Project Review | Review progress and adjust planning. | PMO Team | 2026-06-24 | 2026-07-12
Final Delivery | Final delivery, documentation and training. | PMO Team | 2026-07-13 | 2026-07-30