## GCS
Task | Start Date | End Date | Duration (days)
Authentication & Authorization Management | 2025-12-01 | 2025-12-10 | 7
UI Panels for Mission Planning | 2025-12-11 | 2025-12-22 | 7
Data exchange GCS-UGV | 2025-12-23 | 2026-01-01 | 7
UI Panels for GCS Operations | 2026-01-02 | 2026-01-13 | 7
Notification Messages | 2026-01-14 | 2026-01-23 | 7
Communication & Networking Protocols | 2026-01-27 | 2026-02-05 | 7
Alert Pop-Ups | 2026-02-06 | 2026-02-17 | 7
Data Storage & Back Up | 2026-02-18 | 2026-02-27 | 7
Video Recording / Image Snapshot storage | 2026-03-02 | 2026-03-11 | 7
System Health Assessment | 2026-03-12 | 2026-03-23 | 7
Fault Management | 2026-03-24 | 2026-04-02 | 7
Emergency Management System | 2026-04-03 | 2026-04-14 | 7
Alerts and Notification Management | 2026-04-15 | 2026-04-24 | 7
Video Processing at GCS | 2026-04-27 | 2026-05-07 | 7
Pre- & Post Test of UGV Peripherals | 2026-05-08 | 2026-05-19 | 7
GO / NO GO Decision | 2026-05-20 | 2026-05-29 | 7
Return to Home (RTH) | 2026-06-01 | 2026-06-10 | 7

## VCU
Task | Start Date | End Date | Duration | Owner
Initial Power Check |  |  |  | Sachin Kate / Borse Team
Linux Installation |  |  |  | Sachin Kate / Borse Team
ROS2 Installation |  |  |  | Sachin Kate / Borse Team
ROS2 Workspace configuration |  |  |  | Sachin Kate / Borse Team
Temperature Sensor – technical study |  |  |  | Sachin Kate / Borse Team
Temperature Sensor – SDK setup |  |  |  | Sachin Kate / Borse Team
Temperature Sensor – trial code |  |  |  | Sachin Kate / Borse Team
Temperature Sensor – calibration |  |  |  | Sachin Kate / Borse Team
Temperature Sensor – final code |  |  |  | Sachin Kate / Borse Team
Motor Driver – technical study |  |  |  | Sachin Kate / Borse Team
Motor Driver – SDK setup |  |  |  | Sachin Kate / Borse Team
Motor Driver – trial code |  |  |  | Sachin Kate / Borse Team
Motor Driver – final code |  |  |  | Sachin Kate / Borse Team
3D LIDAR – technical study |  |  |  | Sachin Kate / Borse Team
3D LIDAR – SDK setup |  |  |  | Sachin Kate / Borse Team
3D LIDAR – trial code |  |  |  | Sachin Kate / Borse Team
3D LIDAR – final code |  |  |  | Sachin Kate / Borse Team
Follow Me Tag – technical study |  |  |  | Sachin Kate / Borse Team
Follow Me Tag – SDK setup |  |  |  | Sachin Kate / Borse Team
Follow Me Tag – trial code |  |  |  | Sachin Kate / Borse Team
Follow Me Tag – final code |  |  |  | Sachin Kate / Borse Team
IO module – technical study |  |  |  | Sachin Kate / Borse Team
IO module – SDK setup |  |  |  | Sachin Kate / Borse Team
IO module – trial code |  |  |  | Sachin Kate / Borse Team
IO module – final code |  |  |  | Sachin Kate / Borse Team
EO Sight Camera – technical study |  |  |  | Sachin Kate / Borse Team
EO Sight Camera – SDK setup |  |  |  | Sachin Kate / Borse Team
EO Sight Camera – trial code |  |  |  | Sachin Kate / Borse Team
EO Sight Camera – final code |  |  |  | Sachin Kate / Borse Team
GNSS receiver – technical study |  |  |  | Sachin Kate / Borse Team
GNSS receiver – SDK setup |  |  |  | Sachin Kate / Borse Team
GNSS receiver – trial code |  |  |  | Sachin Kate / Borse Team
EO Sight Camera + encoder – technical study |  |  |  | Sachin Kate / Borse Team
EO Sight Camera + encoder – SDK setup |  |  |  | Sachin Kate / Borse Team
EO Sight Camera + encoder – device testing |  |  |  | Sachin Kate / Borse Team
Drive camera + encoder – technical study |  |  |  | Sachin Kate / Borse Team
Drive camera + encoder – SDK setup |  |  |  | Sachin Kate / Borse Team
Drive camera + encoder – device testing |  |  |  | Sachin Kate / Borse Team
Radio – technical study |  |  |  | Sachin Kate / Borse Team
Radio – SDK setup |  |  |  | Sachin Kate / Borse Team
Radio – trial code |  |  |  | Sachin Kate / Borse Team
BMS – technical study |  |  |  | Sachin Kate / Borse Team
BMS – SDK setup |  |  |  | Sachin Kate / Borse Team
BMS – trial code |  |  |  | Sachin Kate / Borse Team
EO Sight Camera Mast – technical study |  |  |  | Sachin Kate / Borse Team
EO Sight Camera Mast – SDK setup |  |  |  | Sachin Kate / Borse Team
EO Sight Camera Mast – trial code |  |  |  | Sachin Kate / Borse Team
EM brake – technical study |  |  |  | Sachin Kate / Borse Team
EM brake – SDK setup |  |  |  | Sachin Kate / Borse Team
EM brake – trial code |  |  |  | Sachin Kate / Borse Team

## Hardware
Task | Start Date | End Date | Duration
Sensor Calibration & Validation | 2026-01-31 | 2026-02-13 | 14
Environmental Stress Testing | 2026-02-07 | 2026-02-20 | 14
EMI/EMC Testing | 2026-02-14 | 2026-02-27 | 14
Integration with Firmware | 2026-02-21 | 2026-03-06 | 14
Field Integration Testing | 2026-02-28 | 2026-03-13 | 14

## QA
Task | Start Date | End Date | Duration
Test Plan Preparation | 2026-02-07 | 2026-02-20 | 14
Functional & Regression Testing | 2026-02-14 | 2026-02-27 | 14
Bug Triaging & Fix Verification | 2026-02-21 | 2026-03-06 | 14
Final QA Sign-off | 2026-02-28 | 2026-03-13 | 14

## PMO
Task | Start Date | End Date | Duration
Project Kick-off & Resource Allocation | 2025-11-01 | 2025-11-14 | 14
Weekly Sprint Reviews | 2025-11-01 | 2026-04-17 | 168
Mid-Project Review | 2026-01-17 | 2026-01-30 | 14
Final Delivery & Handover | 2026-04-04 | 2026-04-17 | 14