## GCS
Task | Description | Team Involved | Start Date | End Date | Duration (days)
Authentication & Authorization Management | Implement role‑based access control so operators, maintenance staff and users get proper permissions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2025-12-01 | 2025-12-10 | 7
UI Panels for Mission Planning | Mission planning UI with DSM + Survey of India data including preprocessing & visualization. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2025-12-11 | 2025-12-22 | 7
Data exchange GCS-UGV | Real‑time secure bidirectional communication using MAVLink/ROS for telemetry, commands, diagnostics. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2025-12-23 | 2026-01-01 | 7
UI Panels for GCS Operations | Panels for viewing and configuring mission parameters—waypoints, speeds, modes. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-01-02 | 2026-01-13 | 7
Notification Messages | Health monitoring alerts, emergency triggers based on thresholds or operator inputs. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-01-14 | 2026-01-23 | 7
Communication & Networking Protocols | Define command sets, message structures, networking standards for GCS‑UGV. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-01-27 | 2026-02-05 | 7
Alert Pop-Ups | Alerts for mission feasibility, health thresholds, object detection from video. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-02-06 | 2026-02-17 | 7
Data Storage & Back Up | Secure storage with retention policies, automatic backups for mission data. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-02-18 | 2026-02-27 | 7
Video Recording / Image Snapshot storage | Video recording and image snapshots with indexing & timestamp retrieval. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-03-02 | 2026-03-11 | 7
System Health Assessment | Continuous diagnostics, telemetry analysis, health scoring and reporting. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-03-12 | 2026-03-23 | 7
Fault Management | Rule‑based fault classification with severity‑based priorities. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-03-24 | 2026-04-02 | 7
Emergency Management System | Integrate environmental sensors; automated emergency handling for fault events. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-04-03 | 2026-04-14 | 7
Alerts and Notification Management | Central alert system for faults, object detection, emergency conditions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-04-15 | 2026-04-24 | 7
Video Processing at GCS | Real‑time video decoding, stitching, overlays and analytics. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-04-27 | 2026-05-07 | 7
Pre- & Post Test of UGV Peripherals | Automated tests for PTZ camera, motors, battery, GNSS before/after missions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-05-08 | 2026-05-19 | 7
GO / NO GO Decision | Automated go/no‑go based on subsystem health and test results. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-05-20 | 2026-05-29 | 7
Return to Home (RTH) | Automatic RTH on system failures or abort conditions. | Mahadevi Biradar, Satyajeet Deshmukh, Borse Team | 2026-06-01 | 2026-06-10 | 7

## VCU
Task | Description | Team Involved | Start Date | End Date | Duration
Initial Power Check | VCU development activity. | Sachin Kate, Borse Team | 2025-12-01 | 2025-12-08 | 5
Linux Installation | VCU development activity. | Sachin Kate, Borse Team | 2025-12-09 | 2025-12-16 | 5
ROS2 Installation | VCU development activity. | Sachin Kate, Borse Team | 2025-12-17 | 2025-12-24 | 5
ROS2 Workspace configuration | VCU development activity. | Sachin Kate, Borse Team | 2025-12-25 | 2026-01-01 | 5
Temperature Sensor – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-01-02 | 2026-01-09 | 5
Temperature Sensor – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-01-12 | 2026-01-19 | 5
Temperature Sensor – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-01-20 | 2026-01-28 | 5
Temperature Sensor – calibration | VCU development activity. | Sachin Kate, Borse Team | 2026-01-29 | 2026-02-05 | 5
Temperature Sensor – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-02-06 | 2026-02-13 | 5
Motor Driver – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-02-16 | 2026-02-23 | 5
Motor Driver – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-02-24 | 2026-03-03 | 5
Motor Driver – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-03-04 | 2026-03-11 | 5
Motor Driver – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-03-12 | 2026-03-19 | 5
3D LIDAR – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-03-20 | 2026-03-27 | 5
3D LIDAR – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-03-30 | 2026-04-06 | 5
3D LIDAR – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-04-07 | 2026-04-14 | 5
3D LIDAR – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-04-15 | 2026-04-22 | 5
Follow Me Tag – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-04-23 | 2026-04-30 | 5
Follow Me Tag – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-05-04 | 2026-05-11 | 5
Follow Me Tag – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-05-12 | 2026-05-19 | 5
Follow Me Tag – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-05-20 | 2026-05-27 | 5
IO module – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-05-28 | 2026-06-04 | 5
IO module – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-06-05 | 2026-06-12 | 5
IO module – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-06-15 | 2026-06-22 | 5
IO module – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-06-23 | 2026-06-30 | 5
EO Sight Camera – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-07-01 | 2026-07-08 | 5
EO Sight Camera – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-07-09 | 2026-07-16 | 5
EO Sight Camera – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-07-17 | 2026-07-24 | 5
EO Sight Camera – final code | Develop final ROS2-compliant code for integration. | Sachin Kate, Borse Team | 2026-07-27 | 2026-08-03 | 5
GNSS receiver – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-08-04 | 2026-08-11 | 5
GNSS receiver – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-08-12 | 2026-08-19 | 5
GNSS receiver – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-08-20 | 2026-08-27 | 5
EO Sight Camera + encoder – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-08-28 | 2026-09-04 | 5
EO Sight Camera + encoder – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-09-07 | 2026-09-14 | 5
EO Sight Camera + encoder – device testing | Validate real hardware performance and verify output stability. | Sachin Kate, Borse Team | 2026-09-15 | 2026-09-22 | 5
Drive camera + encoder – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-09-23 | 2026-09-30 | 5
Drive camera + encoder – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-10-01 | 2026-10-08 | 5
Drive camera + encoder – device testing | Validate real hardware performance and verify output stability. | Sachin Kate, Borse Team | 2026-10-09 | 2026-10-16 | 5
Radio – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-10-19 | 2026-10-26 | 5
Radio – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-10-27 | 2026-11-03 | 5
Radio – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-11-04 | 2026-11-11 | 5
BMS – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-11-12 | 2026-11-19 | 5
BMS – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-11-20 | 2026-11-27 | 5
BMS – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-11-30 | 2026-12-07 | 5
EO Sight Camera Mast – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2026-12-08 | 2026-12-15 | 5
EO Sight Camera Mast – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2026-12-16 | 2026-12-23 | 5
EO Sight Camera Mast – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2026-12-24 | 2026-12-31 | 5
EM brake – technical study | Review datasheet, understand interfaces, electrical characteristics, communication protocols. | Sachin Kate, Borse Team | 2027-01-01 | 2027-01-08 | 5
EM brake – SDK setup | Install and configure device SDK/library for integration. | Sachin Kate, Borse Team | 2027-01-11 | 2027-01-18 | 5
EM brake – trial code | Write trial code to verify basic communication and functionality. | Sachin Kate, Borse Team | 2027-01-19 | 2027-01-26 | 5

## Hardware
Task | Description | Team Involved | Start Date | End Date | Duration
Sensor Calibration & Validation | Calibrate LiDAR, IMU, GNSS and validate accuracy. | Hardware Team, QA Team | 2026-01-31 | 2026-02-13 | 14
Environmental Stress Testing | Thermal and vibration endurance testing. | Hardware Team, QA Team | 2026-02-07 | 2026-02-20 | 14
EMI/EMC Testing | Test electromagnetic interference and compatibility. | Hardware Team, QA Team | 2026-02-14 | 2026-02-27 | 14
Integration with Firmware | Validate hardware after firmware integration. | Hardware Team, QA Team | 2026-02-21 | 2026-03-06 | 14
Field Integration Testing | System field tests for performance validation. | Hardware Team, QA Team | 2026-02-28 | 2026-03-13 | 14

## QA
Task | Description | Team Involved | Start Date | End Date | Duration
Test Plan Preparation | Create QA plans, test cases and acceptance criteria. | QA Team | 2026-02-07 | 2026-02-20 | 14
Functional & Regression Testing | Run functional and regression test suites. | QA Team | 2026-02-14 | 2026-02-27 | 14
Bug Triaging & Fix Verification | Triage issues and verify fixes. | QA Team | 2026-02-21 | 2026-03-06 | 14
Final QA Sign-off | Prepare documentation and final QA approval. | QA Team | 2026-02-28 | 2026-03-13 | 14

## PMO
Task | Description | Team Involved | Start Date | End Date | Duration
Project Kick-off | Project initiation and resource planning. | PMO Team | 2025-11-01 | 2025-11-14 | 14
Weekly Sprint Reviews | Weekly progress reviews, impediment removal, stakeholder updates. | PMO Team | 2025-11-01 | 2026-04-17 | 168
Mid-Project Review | Review progress and adjust planning. | PMO Team | 2026-01-17 | 2026-01-30 | 14
Final Delivery | Final delivery, documentation and training. | PMO Team | 2026-04-04 | 2026-04-17 | 14