## Aim
Sr.No | Item | Subtasks | Description | Status | Starting Date | End Date
1 | Aim | Ground Based Autonomous Underwater Vehicle | Design and integrate reliable software systems for GBAS, support team collaboration through mentoring and reviews, ensure high-quality, on-time deliveries with strong testing standards. | Inprogress | 01-07-2025 | 31-03-2026
| Aim | Kalyani Autonomous Underwater Vehicle | To lead the design and development of software for the Kalyani AUV, while guiding the team to work together, build technical skills, and keep improving throughout the project. | Inprogress | 01-07-2025 | 31-03-2026

## GB-AUV
No | Subtasks | Description | Status | Start Date | End Date
1 | Authentication & Authorization (SQLite DB) | Role-based access control for operators, maintenance & users | Done | 03-11-2025 | 11-11-2025
2 | Connection Settings | Wi-Fi, Ethernet, Serial settings | In-Progress | 12-11-2025 | 20-11-2025
3 | Power On Self Test | Initial diagnostics | Not Started | 21-11-2025 | 01-12-2025
4 | Pre/Post Test of UGV Peripherals | Testing PTZ, motor, battery, GNSS | Not Started | 02-12-2025 | 10-12-2025
5 | GO / NO GO | Readiness evaluation | Not Started | 11-12-2025 | 19-12-2025
6 | Mission Planning UI | DSM & Survey of India map integration | Not Started | 22-12-2025 | 01-01-2026
7 | GCS Mission Parameters | Waypoints, speed limits | Not Started | 02-01-2026 | 10-01-2026
8 | Communication Protocols | Define commands | Not Started | 13-01-2026 | 21-01-2026
9 | Data Exchange | MAVLink/ROS communication | Not Started | 22-01-2026 | 31-01-2026
10 | Notification Messages | Health alerts & triggers | Not Started | 01-02-2026 | 09-02-2026
11 | Alert Pop-Ups | Health & object detection alerts | Not Started | 12-02-2026 | 20-02-2026
12 | System Health Assessment | Real-time diagnostics | Not Started | 21-02-2026 | 03-03-2026
13 | Fault Management | Fault classification | Not Started | 04-03-2026 | 12-03-2026
14 | Emergency Management | Emergency rule automation | Not Started | 13-03-2026 | 31-03-2026

## KAUV
No | Subtasks | Description | Status | Start Date | End Date
1 | Qt Training | Training given | Completed | 10-Sep-25 | 24-Sep-25
2 | Class Diagram – Mission Editor | Mission planning structure | Completed | 25-Sep-25 | 10-Oct-25
3 | Mission Dialog UI | Tabs: Mission, Live, Replay | Completed | 13-Oct-25 | 17-Oct-25
4 | Settings Panel UI | QLineEdit inputs | Completed | 27-Oct-25 | 31-Oct-25
5 | Waypoints Add | Manual coordinate entry | Completed | 03-Nov-25 | 07-Nov-25
6 | Waypoints Remove | Remove waypoint | Completed | 10-Nov-25 | 12-Nov-25
7 | Map Loading | Display map | Completed | 13-Nov-25 | 14-Nov-25
8 | Waypoints Clear | Clear points | Completed | 17-Nov-25 | 18-Nov-25
9 | Mission Cancel | Reset mission | Completed | 19-Nov-25 | 20-Nov-25
10 | Mission Save | Save mission | Completed | 21-Nov-25 | 24-Nov-25
11 | Code Optimization | Separate scenes | Completed | 25-Nov-25 | 28-Nov-25
12 | Bug Fix Signals | Fix signals/slots | Not Started | 01-Dec-25 | 03-Dec-25
13 | Bug Fix Compilation | Fix references | Not Started | 04-Dec-25 | 05-Dec-25
14 | Upload Mission | Load saved missions | Not Started | 08-Dec-25 | 10-Dec-25
15 | Waypoint Visualization | Coordinates & circle | Not Started | 11-Dec-25 | 15-Dec-25
16 | Live Tracking Plotting | Plot saved points | Not Started | 16-Dec-25 | 19-Dec-25
17 | AUV Simulation | Lat/long & speed | Not Started | 22-Dec-25 | 26-Dec-25
18 | Launch/Abort | Control simulation | Not Started | 29-Dec-25 | 31-Dec-25
19 | Authentication | RBAC SQLite | Not Started | 02-Jan-26 | 10-Jan-26
20 | Navigation HLD | High-level nav | Not Started | 13-Jan-26 | 24-Jan-26
21 | Navigation LLD | Low-level nav | Not Started | 27-Jan-26 | 07-Feb-26
22 | Live Tracking Design | Architecture UI | Not Started | 10-Feb-26 | 21-Feb-26
23 | Replay Module | Replay design | Not Started | 24-Feb-26 | 06-Mar-26
24 | User Testing | Usability testing | Not Started | 09-Mar-26 | 20-Mar-26
25 | Documentation | Manuals & training | Not Started | 23-Mar-26 | 31-Mar-26

## ProcessGoals
Subtask | Description | Status
Modular Software Architecture | UI, mission control, communication | In Progress
Code Quality & Standards | PEP8, MISRA | In Progress
Version Control & CI | Git branching, CI pipelines | In Progress
Testing & Validation | 85%+ coverage | Not Started
Documentation Discipline | Continuous docs updates | In Progress
Agile Development | Bi-weekly sprints | In Progress
Cross-Team Collaboration | Sync with hardware | In Progress
User-Centric Design | Feedback-based UI | Not Started
Performance Optimization | Latency <200ms | Not Started
Fault & Emergency Mgmt | Fault classification | Not Started
Secure Access Control | RBAC + encryption | Completed
Simulation & Replay | Mission rehearsal tools | In Progress
Internal Training | Qt, MAVLink, ROS | Completed
Stakeholder Communication | Demos & reviews | In Progress

## Timeline
Phase | Focus | Timeline
Initiation & Planning | Scope, tools, training | Jul–Sep 2025 (Day 1–45)
Design & Architecture | Class diagrams, UI mockups | Sep–Oct 2025 (Day 46–75)
Core Development | Auth, mission programming | Nov–Jan 2026 (Day 76–135)
System Integration | Data exchange, simulation | Jan–Feb 2026 (Day 136–160)
Testing & Fault Handling | POST, diagnostics | Feb–Mar 2026 (Day 161–180)
Validation & Handover | Testing, docs, training | Mar 2026 (Day 181–191)

## LearningDev
Sr.No | Learning Area | Description | Target Outcome | Status | Timeline
1 | Advanced Qt & PyQt | Model–View, multithreading | Faster UI development | In Progress | Jul 2025 – Dec 2025
2 | Modern C++ | C++17/20, MISRA | Robust modules | In Progress | Jul 2025 – Jan 2026
3 | ROS2 Fundamentals | Nodes, topics | Better integration | Not Started | Jan 2026 – Mar 2026
4 | MAVLink Protocol | Heartbeat, mission protocol | Reliable comms | In Progress | Jan 2026
5 | GIS & Mapping | DSM, Survey maps | Better planning | Not Started | Dec 2025 – Jan 2026
6 | Design Patterns | MVC, Observer | Modular system | In Progress | Jul 2025 – Mar 2026
7 | Unit Testing | PyTest, GoogleTest | 85% coverage | Not Started | Feb–Mar 2026
8 | CI/CD & Git | GitFlow, pipelines | Faster releases | In Progress | Ongoing
9 | Simulation & Control Theory | PID, Kalman | Improved navigation | Not Started | Feb–Mar 2026
10 | System Safety | FMEA, fault tolerance | Emergency mgmt | Not Started | Mar 2026
11 | Mentoring & Leadership | Training peers | Skill growth | Completed | Sep 2025
12 | Documentation Excellence | UML, Sphinx | High-quality docs | In Progress | Jul 2025 – Mar 2026